Rule-Based Indicator Alert Prototype

for Binance Market Data (1h / 1D / 1W)

Project plan, work tickets and rule concepts  |  Backend: Python

# 1. Overview and scope

The prototype lets a user define a simple indicator rule (for example "RSI(14) crosses above 30 on the 1D chart"), click Refresh, and see which rules have triggered. Price data comes from the Binance REST API, is cached in Redis, and indicators are calculated in Python. Rules and alerts are stored in a SQL database. Alerts are shown only in the frontend.

| Area | Decision | Reason |
| --- | --- | --- |
| Data source | Binance REST /api/v3/klines on demand | No WebSocket needed for a prototype; data is fetched when the user clicks Refresh |
| Timeframes | 1h, 1D, 1W | Matches the original requirement |
| Price field | Close price only | Keeps the indicator and rule schema simple |
| Cache | Redis, key klines:{symbol}:{interval}, TTL about 60s | Repeated refresh clicks do not hit Binance rate limits |
| Storage | SQL database (Postgres-compatible via SQLAlchemy) | Rules survive restart; alert history is kept |
| Indicators | SMA, EMA, RSI (each with a length) | Covers MA and RSI rules from the requirement |
| Rules | One rule = one condition (no AND/OR) | Combinations are future work |
| Notifications | Shown in the FE only | No push, Telegram or email |
| Backtest | Not included | Out of scope for the prototype |

# 2. Architecture

Request flow when the user clicks Refresh:

FE (Refresh) -> POST /evaluate

-> for each enabled rule:

read klines from Redis (miss -> fetch Binance REST -> store)

compute indicator on close prices

evaluate operator (gt, lt, cross_above, ...)

save new alerts to SQL (unique per rule + candle)

-> return triggered alerts -> FE displays them

## Suggested stack

- Backend: Python 3.11+, FastAPI + Uvicorn, pydantic, SQLAlchemy

- Data and indicators: requests/httpx, pandas (own SMA/EMA/RSI implementation, or pandas-ta)

- Storage: Redis (kline cache), SQLite or Postgres (rules and alerts)

- Frontend: React (Vite) or a lightweight option such as Vue or Alpine.js

## Suggested folder structure

app/

main.py              # FastAPI app

config.py            # env settings (Redis URL, DB URL, TTL)

binance/client.py    # REST klines + exchangeInfo

cache/redis_cache.py # get/set klines with TTL, stale fallback

indicators/calc.py   # sma, ema, rsi + registry

rules/models.py      # pydantic Rule schema

rules/engine.py      # operators, evaluator, lookback scan

db/models.py         # SQLAlchemy: rules, alerts

api/routes.py        # /rules, /symbols, /evaluate, /alerts, /indicators

tests/

# 3. Work tickets by epic

Estimates are for one developer, in days.

## Epic 1: Setup, Binance REST API and Redis

| ID | Ticket | Done when | Est. (days) |
| --- | --- | --- | --- |
| E1-1 | Set up repo, virtualenv, folder structure, config (.env with Redis and DB URLs), logging | Project runs | 0.5 |
| E1-2 | Study /api/v3/klines for 1h, 1d, 1w and document the response format | Short note with sample payloads | 0.5 |
| E1-3 | REST client: fetch klines for (symbol, interval, limit) | Returns a clean DataFrame Kline will contain data: Long openTime; String open; String high; String low; String close; String volume; Long closeTime; String quoteAssetVolume; | 1 |
| E1-4 | Fetch symbol list (/exchangeInfo, filter quote asset (BUSD, USDC, or USDT) and status ==TRADING) | FE dropdown can use it | 0.5 |
| E1-5 | Redis cache layer: key klines:{symbol}:{interval}, JSON candle list, TTL about 1days; hit returns cache, miss fetches and stores | Repeated refresh clicks do not call Binance within the TTL | 1 |
| E1-6 | Handle Binance errors (HTTP 429/418, invalid symbol, timeout) and fall back to stale Redis data if available | Clear error returned instead of a crash | 0.5 |

Redis notes: the simple option (recommended) stores the whole candle list as one JSON string with a TTL. An incremental option using a sorted set (score = open_time) only fetches the newest candles but needs more code, so it is future work. Cache about 300 candles per key.

## Epic 2: Indicator engine

| ID | Ticket | Done when | Est. (days) |
| --- | --- | --- | --- |
| E2-1 | SMA(length) and EMA(length) on close | Matches TradingView within rounding | 0.5 |
| E2-2 | RSI(length) with Wilder smoothing on close | Matches TradingView | 1 |
| E2-3 | Indicator registry (sma, ema, rsi with length) | New indicator added in one place | 0.5 |
| E2-4 | Unit tests on a known dataset; warm-up check (error if too few candles for the length) | Tests pass | 1 |

## Epic 3: Rule engine (single rule)

| ID | Ticket | Done when | Est. (days) |
| --- | --- | --- | --- |
| E3-1 | Rule schema (pydantic) with one condition: symbol, timeframe, indicator (type, length), operator, target (number or another indicator), candle_mode (closed only / include current) | Invalid rules rejected with clear errors | 0.5 |
| E3-2 | Operators: gt, lt, gte, lte, cross_above, cross_below | Unit tests cover equal values and nulls | 1.5 |
| E3-3 | Evaluator for a single rule with both candle modes (drop the last open candle, or keep it) | Correct results on test data | 1 |
| E3-4 | Lookback scan: check the last N candles so crosses between refreshes are not missed | Returns every trigger within N candles | 0.5 |
| E3-5 | SQL schema (SQLAlchemy): rules (id, symbol, timeframe, indicator, length, operator, target, candle_mode, enabled, created_at) and alerts (id, rule_id, symbol, timeframe, candle_open_time, indicator_value, target_value, triggered_at) | Tables created on startup; rules survive restart | 1 |
| E3-6 | Dedupe with a unique constraint on (rule_id, candle_open_time) in alerts | Repeated Refresh never creates the same alert twice | 0.5 |

## Epic 4: API and frontend

| ID | Ticket | Done when | Est. (days) |
| --- | --- | --- | --- |
| E4-1 | FastAPI endpoints: CRUD /rules, GET /symbols, POST /evaluate, GET /alerts, GET /indicators/{symbol}?timeframe= | Swagger docs work | 1.5 |
| E4-2 | FE rule form: symbol, timeframe (1h/1D/1W), indicator (SMA/EMA/RSI), length, operator (above/below/cross above/cross below), value or second indicator, candle mode | User can create a rule without JSON | 2.5 |
| E4-3 | FE rule list with enable/disable and delete | Works end to end | 1 |
| E4-4 | FE Refresh button and alert panel (symbol, rule, indicator value, candle time, loading and error states) | Clicking Refresh shows new alerts | 1 |
| E4-5 | FE alert history and a table of current indicator values per symbol | Helps users pick sensible thresholds | 1 |

## Epic 5: Testing and documentation

| ID | Ticket | Done when | Est. (days) |
| --- | --- | --- | --- |
| E5-1 | Integration tests with simulated candles that force each operator to fire (mock Binance client; test Redis and DB) | Every operator verified | 1.5 |
| E5-2 | Manual end-to-end test with real Binance data (loose rule first, then a strict one) | Alerts appear in the FE | 0.5 |
| E5-3 | README with setup steps (including how to start Redis) | Teammates can run the project | 0.5 |

# 4. Schedule

Total is roughly 22 days of work, about 3 weeks for one developer.

| Week | Scope | Milestone |
| --- | --- | --- |
| Week 1 | Epic 1 and Epic 2 | Klines cached in Redis; RSI/SMA/EMA computed correctly |
| Week 2 | Epic 3 and E4-1 (API) | A rule can be created through the API and /evaluate returns alerts |
| Week 3 | Rest of Epic 4, Epic 5, report | Working demo |

# 5. Indicator and rule concepts

## 5.1 What the length (period) means

RSI and RSI(14) are the same indicator. The number is the period (length): how many candles the indicator looks back over. On a 1D chart one candle is one day, so RSI(14) looks at about 14 days. When people say "RSI" they usually mean RSI(14), the default on TradingView and Binance.

| Length | Reaction | Signals | Noise |
| --- | --- | --- | --- |
| Short (e.g. 7) | Fast, sensitive | Many | More false signals |
| Default (14) | Balanced | Moderate | Moderate |
| Long (e.g. 21) | Slow, smooth | Few | Fewer false signals |

The same idea applies to moving averages: SMA(50) is the average close of the last 50 candles. RSI(14) is calculated as RS = average gain / average loss, then RSI = 100 - 100 / (1 + RS), always between 0 and 100. Use Wilder smoothing so values match TradingView. At least length + 1 candles are needed, and about 300 are recommended so the smoothing settles.

## 5.2 Operators: above/below vs cross above/cross below

A cross compares two lines over two candles. The target can be a constant number (RSI crosses above 30) or another indicator (SMA(50) crosses above SMA(200)).

| Operator | Meaning | Fires when |
| --- | --- | --- |
| gt (above) | A is greater than B right now | Every candle while A > B (a state) |
| cross_above | A just became greater than B | Only on the candle where it flips (an event) |

Example with RSI and the level 30:

| Day | RSI | rsi > 30 | rsi cross_above 30 |
| --- | --- | --- | --- |
| 1 | 25 | no | no |
| 2 | 28 | no | no |
| 3 | 33 | yes | yes (28 to 33 crossed 30) |
| 4 | 38 | yes | no |
| 5 | 41 | yes | no |

Logic using the previous candle (prev) and the latest candle (cur):

cross_above:  prev_A <= prev_B  AND  cur_A > cur_B

cross_below:  prev_A >= prev_B  AND  cur_A < cur_B

Crosses are better for alerts because they fire once instead of on every candle. If the target is a constant, B is the same number on both candles. Because only close price is used, add a special left-side type close (or price) so rules like "price crosses above SMA(20)" are possible.

## 5.3 Rule schema examples

// RSI crosses above a number

{

"symbol": "BTCUSDT", "timeframe": "1d",

"indicator": {"type": "rsi", "length": 14},

"operator": "cross_above",

"target": 30,

"candle_mode": "closed"

}

// SMA 50 crosses above SMA 200 (golden cross)

{

"symbol": "BTCUSDT", "timeframe": "1d",

"indicator": {"type": "sma", "length": 50},

"operator": "cross_above",

"target": {"type": "sma", "length": 200},

"candle_mode": "closed"

}

In the FE form, show the target as a choice between Value (number input) or Indicator (type and length dropdowns). The operator dropdown has the same four options for both.

## 5.4 Starter rule ideas (single condition)

| # | Rule | Meaning |
| --- | --- | --- |
| 1 | RSI(14) crosses above 30 | Oversold bounce (potential buy) |
| 2 | RSI(14) crosses below 70 | Overbought reversal (potential sell) |
| 3 | RSI(14) crosses above 50 | Momentum turning bullish |
| 4 | RSI(14) crosses below 50 | Momentum turning bearish |
| 5 | Close crosses above SMA(200) | Entering a bull regime |
| 6 | Close crosses below SMA(200) | Entering a bear regime |
| 7 | SMA(50) crosses above SMA(200) | Golden cross |
| 8 | SMA(50) crosses below SMA(200) | Death cross |
| 9 | EMA(12) crosses above EMA(26) | Fast trend change up |
| 10 | Close crosses above / below SMA(20) | Short-term trend change |

RSI 30/70 works poorly in strong trends, since RSI can stay above 70 or below 30 for weeks. Combined rules such as "close > SMA200 AND RSI crosses above 30" are a good future extension once AND/OR is supported.

# 6. Things to watch

- Candle timing: 1h candles close at the top of each hour (UTC), 1D at 00:00 UTC, 1W on Monday 00:00 UTC. Compute in UTC and display in the user timezone.

- Open candle: the last candle returned by REST is still open. Dropping it gives closed-candle mode; keeping it gives live mode, whose signals can appear and disappear before the candle closes. Label the mode on every alert.

- Missed signals: with on-demand polling, crosses between refreshes can be missed, which is why the lookback scan (E3-4) is kept.

- Duplicate alerts: the same data is re-evaluated on every click, so the unique constraint (E3-6) is essential.

- Warm-up: SMA(200) on 1W needs about 4 years of data. Show a clear error if there are not enough candles for the chosen length.

- Region restrictions: api.binance.com may be blocked in some regions. data-api.binance.vision serves public market data, and the testnet can be used for development.

- Rate limits: the Redis cache and the stale-data fallback protect against HTTP 429/418 responses.

# 7. Report notes

## Suggested report title

Design and Implementation of a Rule-Based Indicator Alert System for Binance Daily Market Data

## Architecture description

"On-demand polling with a Redis cache and a SQL store for rules and alerts."

## Limitations

- Single-condition rules only

- Close price only

- No streaming; data is refreshed on demand

- No backtesting, so signal quality is not validated

## Future work

- AND/OR rule combinations and other price sources (open, high, low, volume)

- WebSocket streaming for real-time evaluation

- Push notifications (Telegram, email, webhook)

- Backtesting module to measure how often each rule fires and what price does afterwards

- Incremental Redis storage (sorted set) to fetch only new candles

Note: indicator signals are alerts, not predictions or trading advice.